## Work Plan
NAME OF CLUB Timber Tour Work Plan 2018
Task | Timeline | Who is responsible | Performance Indicators | Status | Notes | Evaluation Review
Task that needs to be completed | Expected Start and Finish Dates | Who has been tasked? | Activities that have demonstrated task is complete | Not Complete, Ongoing, Completed | Any notes on task | Evaluation score is a numerical score: 1. Did not meet expectation 2.Meets expectations 3. Exceeds Expectations
Review Google Working Folder
Determine your own Event Schedule | By Sept 1
Ensure all major officials understand the scope of their responsibilities
Review Volunteers needed for Timber Tour with Volunteer Coordinator
Set Schedule for Organizing Committee (OC) meetings, minimum 4 meetings
Conduct 4 meetings
Send Event Manager Club and Resort Logo in eps or pdf format
Assist Event Manager to liaison with Ski Resort to establish lift ticket prices for: ATHLETES | Early October
Assist Event Manager to liaison with Ski Resort to establish lift ticket prices for: COACHES | Early October
Assist Event Manager to liaison with Ski Resort to establish lift ticket prices for: VOLUNTEERS
Assist Event Manager to liaison with Ski Resort to establish lift ticket prices for: FAMILY | October
Review Event Course Specifications | January
Get a quote on local scaffolding ( Try 2 scaffolding ) | November |  |  | To do
Determine logistics for Scaffolding | November - December |  |  |  | Dan and Jane discussed 2 scaffolding set ups to reduce volunteer demand at end of day on Saturday. Dan will investiage costs. Need to agree on sizes.
Determine competition run closures from public | Closer to event |  |  |  | Make sure clear about Park, Macdonald is no problem
Ensure Lift/T-bar/chairlift is open in time for training
Investigate local hotel options | Before Nov 20 |  |  | complete | Booking deadline date:
Secure registration area for training and competition days | early october |  |  | To do
Organize a quiet scoring area with access to power and internet ( if available) | FO trailer not suitable |  |  | To do | confirm chalet or hut for moguls - month before
Liaison with Event Manager and Resort to organize appropriate number of patrollers (2 Patrollers needed on event date) | November |  |  | To do | Call to make sure Patrollers know and this is on their scheudle so they can be prepared. Jane to give Jane #
Send Patroller schedule of event (Times when they are needed) | few weeks before |  |  | To do
Create EAP (Emergency Action Plan) Closest Hospital | Thursday before (once registration is complete) | Dan? |  | To do
Prepare transportation arrangements to get judges to stand in AM, down before lunch and after lunch (i.e., ski tickets, snowmobile, easy walk) | 1 month out |  |  | To do
Provide chairs and tables for judges, timer and announcer | 3 weeks out!
Arrange to have an Operations Employee available to help on competition mornings |  |  |  | Necessary? | Not sure if this is needed
Determine if scaffolding is needed
Order scaffolding (FSO has scaffolding in SOR, but probably better to get in ottawa) | 1 month out
Schedule the Time and Volunteers to help with set up of scaffolding | 1 month out
Liaison with Event Manager to arrange lunches on comp days for judges and major officials | Late November
Need an announcer
Arrange how athletes will get tickets, where to go. | January
Confirm Medal Ceremony location ( Same as last year)
Direct Volunteers to Level 1 - Volunteer Orientation online
Discuss Volunteer Recruitment, Online Doc (google forum)
Review Volunteer schedule, created by Event Manager
Work with Event Manager on Volunteer recruitment email copy
Send out information document on what each volunteer will be required to do competition day
Determine if Media Plan is required
Discuss Press release timeline
Prepare on-hill transportation arrangements for training and competition day(s) (snowmobiles etc)
Determine if there will be a banquet/apres
Determine banquet needs
Volunteer Appreciation
Determine tear down schedule and requirements
Touch base on equipment
Explore back up plans for wind(slopestyle) - make clear options and communication plan in invite

## Equipment
Equipment List
What FO will provide
Task | Timeline | Who is responsible | Status | Notes | Review
An invitation and registration link |  | FO
Providing a Judge Panel | Early December | FO
Providing a Technical Delegate | Early December | FO
Help with Volunteer Coordinator | Ongoing | FO
Help facilitate volunteer training | Ongoing | FO
Medals | Bring to event | FO
Prizing | Bring to event | FO
Awards Backdrop | Bring to event | FO
Bibs | Bring to event | FO
Help and Labour on Comp Day ( Jeff, Kelsey) | Bring to event | FO
Competition Radios | bring to event | FO
Registration Lists | bring to event | FO
Tents for Start Area | bring to event | FO
Tent for Judges | bring to event | FO
Drills (2) | Bring to event | FO
Video Camera | Bring to event | FO
Sound System | Bring to event | FO
Timing Equipment | Bring to event | FO
Stakes for timing equipment | Bring to event | FO
Additional Equipment Needed
Equipment | Quantity | Who is responsible | Status | Notes | Review
Fencing for crowd control
Heaters for Judges
Red Control Gates | 22
Blue Control Gates | 22
Bamboos | 200
Flourescent Tape | 3000'
Snow Fencing | TBD
Willy Bags | TBD
Generator | 1
Fuel | AR
Water for jump building | 1 Bucket
Square nose shovels | 8
Sprayer for jump building (MO) | 1
Square nose shovels | 4
Pointed nose shovels | 4
Pointed nose shovels | 4
Large square nose shovels | 1
Snow scoop | 1
Rake | 2
Pick/grubhoe | 4
Drill | 1
30 mm drill bit | 1
Rope | 1000'
Start flags | 2
Scaffolding
Plywood bases | 12
Tarps | 1 - 2
Platform for Sound | 1
Salt | boxes |  |  | Buy week of event if needed
Ammonium Nitrate | 10 bags |  |  | Buy week of event if needed
Dye Sprayer | 1
Dye Tablets | 2 jars
Folding Tables | 3
Chairs | 2
Jump Form | 1
Antifreeze | 4 Jugs
Inclinometer | 1
Ratchet straps | 4
Level | 1
Bungees | 8
iPod Charger & Cable
Headphone cord & extension

## Contact Information
First | Last | Position | Avaialble Dates to help | Committee | Jury | Affiliation | e-mail | Mobile | Notes | Legend
Jane | Curtis | Event Manager | All | Yes |  | FO | jane@freestyleontario.ski | 705-441-3925
|  | OC Chair |  | Yes | No
|  | Chief of Course (MO) |  | Yes | No
|  | Volunteer Coordinator |  | Yes | No
CEO and GM
|  | Chief of Comp |  |  | Yes
Co Chair